## Instructions
Case Study Project Tracker
Java Full Stack Training — Capstone Case Study
How to use this workbook
1. Go to the 'Task Tracker' sheet. Each trainee/team lists the tasks (modules, features, sub-tasks) for their case study there — similar to a sprint backlog in a real software team.
2. Update your task's Status, % Complete, and Hours Spent regularly (daily/every alternate day) — do not wait until the deadline.
3. Use the 'Daily Work Log' sheet every working day to record what you did, like a standup update: Yesterday's work, Today's plan, and any blockers.
4. The 'Dashboard' sheet updates automatically from the Task Tracker sheet — do not edit it directly.
5. Cells shaded light yellow are example rows — replace them with your own data. Do not delete the header rows.
Column & Status Legend (Task Tracker sheet)
Status values: Not Started, In Progress, Blocked, In Review, Completed
Priority values: High, Medium, Low
% Complete: enter a whole number between 0 and 100 (e.g., 50 for 50%).
Hours Estimated / Hours Spent: enter numeric hours (e.g., 4, 6.5).
Remarks / Blockers: mention any dependency, doubt, or issue blocking progress — leave blank if none.
Column Legend (Daily Work Log sheet)
Fill one row per person per working day. Task ID should match the Task Tracker sheet where applicable.
Conventions used in this workbook
Yellow fill = example row / cells you should edit or replace with your own data.
White/grey rows = your data entry rows (add as many as needed).
Dashboard values and charts = auto-calculated, formula-driven — do not overwrite.

## Task Tracker
Case Study Task Tracker
Update Status, % Complete and Hours Spent regularly. See 'Instructions' sheet for the legend.
Task ID | Module / Feature | Task Description | Assigned To | Priority | Status | Start Date | Due Date | Est. Hours | Hours Spent | % Complete | Remarks / Blockers | Last Updated
T-001 | Entity | approval , login,auditlog | Neelesh | Medium | Completed | 2026-10-01 |  | 6 | 2 | 90 | Completed | 2026-10-02
T-002 | Entity | leaveapplication , leave balance | Muskan | Medium | Completed | 2026-10-01 |  | 6 | 2:30 | 80 | Completed | 2026-10-02
T-003 | Entity | notification , holiday | Nitish | Medium | Completed | 2026-10-01 |  | 6 | 1:40 | 70 | Completed | 2026-10-02
T-004 | Entity | Employee,LeaveType | Anjanayak | Medium | Completed | 2026-10-01 |  | 6 | 1:40 | 90 | Completed | 2026-10-02
T-005 | controller | Employee,Manager | Neelesh | High | Completed | 2026-10-02 |  | 6 | 3 | 78 | Completed | 2026-10-02
T-006 | controller | hR | Nitish | Medium | Completed | 2026-10-02 |  | 6 | 3 | 88 | Completed | 2026-10-02
T-007 | controller | leave,Login | Muskan | High | Completed | 2026-10-02 |  | 6 | 3:30 | 78 | Completed | 2026-10-02
T-008 | MainApplication | Main | Neelesh | medium | Completed | 2026-10-02 |  | 5 | 3 | 80 | Completed | 2026-10-02
T-009 | dto | approval,loginrequest,loginresponse | neelesh | Medium | Completed | 2026-10-02 |  | 7 | 3 | 75 | Completed | 2026-10-02
T-010 | dto | leaverequest | nitish | Medium | Completed | 2026-10-02 |  | 7 | 4:15 | 70 | Completed | 2026-10-02
T-011 | service | approval,login,leavescheduler,ApprovalServiceImpl,LeaveServiceImpl,LoginServiceImpl | neelesh | High | Completed | 2026-10-02 |  | 6 | 5 | 80 | Completed | 2026-10-02
T-012 | service | notification,holiday,NotificationServiceImpl,HolidaysServiceImpl | nitish | High | Completed | 2026-10-03 |  | 6 | 4:30 | 75 | Completed | 2026-10-04
T-013 | service | leavetype , leave balance,LeaveTypeServiceImpl,LeaveBalanceServiceImpl | muskan | Medium | Completed | 2026-10-03 |  | 6 | 5 | 80 | Completed | 2026-10-04
T-014 | service | Employee,Leave,EmployeeServiceImpl,LeaveServiceImpl | anju | Medium | Completed | 2026-10-03 |  | 6 | 4:30 | 90 | Completed | 2026-10-04
T-015 | repository | approval , login | neelesh | High | Completed | 2026-10-03 |  | 6 | 5:15 | 85 | Completed | 2026-10-04
T-016 | repository | notification , holiday | nitish | Medium | Completed | 2026-10-03 |  | 6 | 3:50 | 80 | Completed | 2026-10-04
T-017 | repository | leavetype , leave balance,AuditLog | muskan | High | Completed | 2026-10-03 |  | 7 | 6 | 90 | Completed | 2026-10-04
T-018 | repository | employee | anju | Medium | Completed | 2026-10-03 |  | 7 | 5 | 75 | Completed | 2026-10-04
T-019 | Enums | Leavestatus,Notificationtype,role | anju | High | Completed | 2026-10-03 |  | 7 | 5:15 | 80 | Completed | 2026-10-04
T-020 | Exception | BussinessException,GobalExceptionHandler,resourceNotFountException | muskan | Medium | Completed | 2026-10-03 |  | 7 | 5 | 70 | Completed | 2026-10-04
T-021 | Frontend | Allocate,ApplyLeave,Approvals,Dashboard,EmployeeDachboard,Employee | Neelesh | Medium | Completed | 2026-10-04 |  | 7 | 6:30 | 90 | Completed | 2026-10-05
T-022 | Frontend | Holidays,HRDashboard,LeaveTypes,ManagerDashBoard,MyLeaves,Notifications,Register,team | Muskan | Medium | Completed | 2026-10-04 |  | 7 | 6 | 85 | Completed | 2026-10-05

## Daily Work Log
Daily Work Log
Fill one row per person per working day — like a daily standup update.
Date | Participant Name | Task ID | Work Done Today | Hours Spent | Status | Blockers / Issues | Plan for Tomorrow
2026-10-01 | Neelesh | T-001 | approval , login,auditlog | 2 | Completed | None | Employee,Manager
2026-10-01 | Muskan | T-002 | leaveapplication , leave balance | 2:30 | Completed | None | leave,Login
2026-10-01 | Nitish | T-003 | notification , holiday | 1:40 | Completed | None | hR
2026-10-01 | Anjanayak | T-004 | Employee,LeaveType | 1:40 | Completed | None | Employee,Leave,EmployeeServiceImpl,LeaveServiceImpl
2026-10-02 | Neelesh | T-005 | Employee,Manager | 3 | Completed | None | Main
2026-10-02 | Nitish | T-006 | hR | 3 | Completed | None | leaverequest
2026-10-02 | Muskan | T-007 | leave,Login | 3:30 | Completed | None | leavetype , leave balance,LeaveTypeServiceImpl,LeaveBalanceServiceImpl
2026-10-02 | Neelesh | T-008 | Main | 3 | Completed | None | approval,loginrequest,loginresponse
2026-10-02 | neelesh | T-009 | approval,loginrequest,loginresponse | 3 | Completed | None | approval,login,leavescheduler,ApprovalServiceImpl,LeaveServiceImpl,LoginServiceImpl
2026-10-02 | nitish | T-010 | leaverequest | 4:15 | Completed | None | notification,holiday,NotificationServiceImpl,HolidaysServiceImpl
2026-10-02 | neelesh | T-011 | approval,login,leavescheduler,ApprovalServiceImpl,LeaveServiceImpl,LoginServiceImpl | 5 | Completed | None | approval , login
2026-10-03 | nitish | T-012 | notification,holiday,NotificationServiceImpl,HolidaysServiceImpl | 4:30 | Completed | None | notification , holiday
2026-10-03 | muskan | T-013 | leavetype , leave balance,LeaveTypeServiceImpl,LeaveBalanceServiceImpl | 5 | Completed | None | leavetype , leave balance,AuditLog
2026-10-03 | Anjanayak | T-014 | Employee,Leave,EmployeeServiceImpl,LeaveServiceImpl | 4:30 | Completed | None | employee
2026-10-03 | neelesh | T-015 | approval , login | 5:15 | Completed | None | Allocate,ApplyLeave,Approvals,Dashboard,EmployeeDachboard,Employee
2026-10-03 | nitish | T-016 | notification , holiday | 3:50 | Completed | None | Run the program and find the error
2026-10-03 | muskan | T-017 | leavetype , leave balance,AuditLog | 6 | Completed | None | BussinessException,GobalExceptionHandler,resourceNotFountException
2026-10-03 | Anjanayak | T-018 | employee | 5 | Completed | None | Leavestatus,Notificationtype,role
2026-10-03 | Anjanayak | T-019 | Leavestatus,Notificationtype,role | 5:15 | Completed | None | Run the program and find the error
2026-10-03 | muskan | T-020 | BussinessException,GobalExceptionHandler,resourceNotFountException | 5 | Completed | None | Holidays,HRDashboard,LeaveTypes,ManagerDashBoard,MyLeaves,Notifications,Register,team
2026-10-04 | Neelesh | T-021 | Allocate,ApplyLeave,Approvals,Dashboard,EmployeeDachboard,Employee | 6:30 | Completed | None | Run the program and find the error
2026-10-04 | Muskan | T-022 | Holidays,HRDashboard,LeaveTypes,ManagerDashBoard,MyLeaves,Notifications,Register,team | 6 | Completed | None | Run the program and find the error

## Dashboard
Project Tracker Dashboard
Auto-calculated from the 'Task Tracker' sheet — do not edit these cells.
Task Status Summary
Total Tasks | 22
Not Started | 0
In Progress | 0
Blocked | 0
In Review | 0
Completed | 22
Effort Summary
Total Est. Hours | 139
Total Hours Spent | 47.809
Avg. % Complete | 80.8636
Status | Count | Metric | Hours
Not Started | 0 | Est. Hours | 139
In Progress | 0 | Spent Hours | 47.809
Blocked | 0
In Review | 0
Completed | 22